## Overview
Project Name |  |  | Brain2Machine Interface
Current Project Week |  |  | 12
Project Type | PRO-3 |  | 4 |  | ECTS
Project Life Span |  |  | 12 |  | Weeks
Resulting Workload |  |  | 6000 |  | Minutes
|  |  | 100 |  | Hours
|  |  | ca. | 8.3333 | Hours per week
Current Overview | [5 empty] | Complete Overview
Week Nr. |  | 12 | Debit Hours (as planned) | Actual Hours | Difference | Week Overview | 16.04 - 22.04.2018 | 23.04 - 29.04.2018 | 30.04 - 06.05.2018 | 07.05 - 13.05.2018 | 14.05 - 20.05.2018 | 21.05 - 27.05.2018 | 28.05 - 03.06.2018 | 04.06 - 10.06.2018 | 11.06 - 17.06.2018 | 18.06 - 24.06.2018 | 25.06 - 01.07.2018 | 02.07 - 08.07.2018 | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | Sum | Debit Hours - Complete - | Difference - Complete -
[7 empty] | Week 01 | Week 02 | Week 03 | Week 04 | Week 05 | Week 06 | Week 07 | Week 08 | Week 09 | Week 10 | Week 11 | Week 12 | R-Week 13 | R-Week 14 | R-Week 15 | R-Week 16 | R-Week 17 | R-Week 18 | R-Week 19 | R-Week 20
Boris Fuchs |  |  | 0 | 76 | 76 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -24
[6 empty] | Actual | 4 | 10 | 6 | 5 | 0 | 5 | 6 | 0 | 12 | 5 | 16 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76
[6 empty] | Difference | 4 | 10 | 6 | 5 | 0 | 5 | 6 | 0 | 12 | 5 | 16 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76
Paul Schmutz |  |  | 0 | 81 | 81 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -19
[6 empty] | Actual | 5 | 10 | 6 | 6 | 0 | 12 | 8 | 0 | 9 | 7 | 11 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
[6 empty] | Difference | 5 | 10 | 6 | 6 | 0 | 12 | 8 | 0 | 9 | 7 | 11 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
---- |  |  | 0 | 0 | 0 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
---- |  |  | 0 | 0 | 0 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
---- |  |  | 0 | 0 | 0 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Std-A
Time Recording
Boris Fuchs
Week 01 |  |  |  | 16.04 - 22.04.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 | EEG testen | 120 | Minutes
3 | Online Recherche EEG | 120 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 4 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 23.04 - 29.04.2018
Nr | Type of Work | Duration |  | Comment
1 | EEG Experiment + Matlab | 450 | Minutes | Read EEG Data
2 | Online Recherche EEG | 120 | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 10 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 30.04 - 06.05.2018
Nr | Type of Work | Duration |  | Comment
1 | Meeting | 30 | Minutes
2 | Matlab Testdaten | 300 | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 6 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 07.05 - 13.05.2018
Nr | Type of Work | Duration |  | Comment
1 | Matlab Testdaten | 300 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 5 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 14.05 - 20.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 21.05 - 27.05.2018
Nr | Type of Work | Duration |  | Comment
1 | EEG Experiment | 300 | Minutes | Emotiv Insight testen, Versuch Open EEG mit Emotiv Positionierung
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 5 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 28.05 - 03.06.2018
Nr | Type of Work | Duration |  | Comment
1 | Beispielapplikation (Space Invaders) | 120 | Minutes
2 | Emotiv Insights testen | 240 | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 6 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 04.06 - 10.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 11.06 - 17.06.2018
Nr | Type of Work | Duration |  | Comment
1 | Java Sample Game | 380 | Minutes
2 | Mindstorms Greifarm bauen | 360 | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 12 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 18.06 - 24.06.2018
Nr | Type of Work | Duration |  | Comment
1 | Requirements Specification | 300 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 5 | Hours
Geplant |  | 0 | Hours
Week11 |  |  |  | 25.06 - 01.07.2018
Nr | Type of Work | Duration |  | Comment
1 | Status Meeting | 45 | Minutes
2 | Sample app | 300 | Minutes | Tweak gesture detection, program lego mindstorms
3 | User guide und Plakat | 300 | Minutes
4 | Mindstorms Vorbereitungen | 300 | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 16 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 02.07 - 08.07.2018
Nr | Type of Work | Duration |  | Comment
1 | Projektpräsentation und Finalisieren | 420 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 7 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-B
Time Recording
Paul Schmutz
Week 01 |  |  |  | 16.04 - 22.04.2018
Nr | Type of Work | Duration |  | Comment
1 | EEG testen | 120 | Minutes
2 | Zeitplan, Req. Spec | 30 | Minutes
3 | Online Recherche EEG | 120 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 5 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 23.04 - 29.04.2018
Nr | Type of Work | Duration |  | Comment
1 | EEG Experiment + Matlab | 450 | Minutes | Read EEG Data
2 | Online Recherche EEG | 120 | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 10 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 30.04 - 06.05.2018
Nr | Type of Work | Duration |  | Comment
1 | Meeting | 30 | Minutes
2 | Matlab Testdaten | 300 | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 6 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 07.05 - 13.05.2018
Nr | Type of Work | Duration |  | Comment
1 | Requirements Specification | 30 | Minutes
2 | Matlab Testdaten | 300 | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 6 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 14.05 - 20.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 21.05 - 27.05.2018
Nr | Type of Work | Duration |  | Comment
1 | EEG Experiment | 300 | Minutes | Emotiv Insight testen, Versuch Open EEG mit Emotiv Positionierung
2 | EEG Matlab processing | 400 | Minutes | Testdaten aufzeichnen, Versuch Extraktion von Eigenschaften verschiedener Gesten
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 12 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 28.05 - 03.06.2018
Nr | Type of Work | Duration |  | Comment
1 | Testdaten erfassen | 60 | Minutes | EEG Gerät bugt, Testdaten haben anderes Aussehen als gewöhnlich
2 | Problembesprechung | 45 | Minutes | mit Prof. Ostermayer
3 | Fehlerbehebung Matlab | 120 | Minutes
4 | Emotiv Insights testen | 240 | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 8 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 04.06 - 10.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 11.06 - 17.06.2018
Nr | Type of Work | Duration |  | Comment
1 | Requirements Specification | 80 | Minutes
2 | Java Reader | 120 | Minutes
3 | Java Reader | 360 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 9 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 18.06 - 24.06.2018
Nr | Type of Work | Duration |  | Comment
1 | Java Reader | 60 | Minutes | left, right gesture
2 | Frequency Range Gesture | 45 | Minutes
3 | Tweak gesture dection, close mouth gesture | 300 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 7 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 25.06 - 01.07.2018
Nr | Type of Work | Duration |  | Comment
1 | Status meeting | 45 | Minutes
2 | Sample app | 360 | Minutes | Tweak gesture detection, program lego mindstorms
3 | Documentation | 240 | Minutes | Requirements specification, abstract, code documentation
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 11 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 02.07 - 08.07.2018
Nr | Type of Work | Duration |  | Comment
1 | Projektpräsentation und Finalisieren | 420 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 7 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-C
Time Recording
----
Week 01 |  |  |  | 16.04 - 22.04.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 23.04 - 29.04.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 30.04 - 06.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 07.05 - 13.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 14.05 - 20.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 21.05 - 27.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 28.05 - 03.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 04.06 - 10.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 11.06 - 17.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 18.06 - 24.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 25.06 - 01.07.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 02.07 - 08.07.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-D
Time Recording
----
Week 01 |  |  |  | 16.04 - 22.04.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 23.04 - 29.04.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 30.04 - 06.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 07.05 - 13.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 14.05 - 20.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 21.05 - 27.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 28.05 - 03.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 04.06 - 10.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 11.06 - 17.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 18.06 - 24.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 25.06 - 01.07.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 02.07 - 08.07.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-E
Time Recording
----
Week 01 |  |  |  | 16.04 - 22.04.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 23.04 - 29.04.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 30.04 - 06.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 07.05 - 13.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 14.05 - 20.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 21.05 - 27.05.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 28.05 - 03.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 04.06 - 10.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 11.06 - 17.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 18.06 - 24.06.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 25.06 - 01.07.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 02.07 - 08.07.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## dynamic Data
Project Weeks
Week 1 | 16.04 - 22.04.2018
Week 2 | 23.04 - 29.04.2018
Week 3 | 30.04 - 06.05.2018
Week 4 | 07.05 - 13.05.2018
Week 5 | 14.05 - 20.05.2018
Week 6 | 21.05 - 27.05.2018
Week 7 | 28.05 - 03.06.2018
Week 8 | 04.06 - 10.06.2018
Week 9 | 11.06 - 17.06.2018
Week 10 | 18.06 - 24.06.2018
Week 11 | 25.06 - 01.07.2018
Week 12 | 02.07 - 08.07.2018
R-Week 13 | DD.MM - DD.MM.YYYY
R-Week 14 | DD.MM - DD.MM.YYYY
R-Week 15 | DD.MM - DD.MM.YYYY
R-Week 16 | DD.MM - DD.MM.YYYY
R-Week 17 | DD.MM - DD.MM.YYYY
R-Week 18 | DD.MM - DD.MM.YYYY
R-Week 19 | DD.MM - DD.MM.YYYY
R-Week 20 | DD.MM - DD.MM.YYYY
Participantes
Std-A | Boris Fuchs
Std-B | Paul Schmutz
Std-C | ----
Std-D | ----
Std-E | ----
Project Types
PRO-1
PRO-2
PRO-3
PRO-4
PRO-2-M
PRO-3-M